## Product backlog
Product Backlog

Name	Est	Imp	How to test	Notes

20 Jun – 15 Aug
View lastest jobs from top ruby sites	11	100	Browse to site / - home page should have latest jobs

Search top ruby sites jobs for last 3 months	20	100	Browse to site / - enter some text in search box / - results should be by date / - results should have text in job post / - there should be an excerpt with matching text / - jobs should go back 3 months
	31

Download a feed for latest jobs	3	50	Browse to site / - there should be an rss feed for latest jobs / - download feed with a feed reader / - make sure it updates daily

Create a feed of search results	3	40	Browse to site / - enter some text in search box / - results should have an rss feed matching results / - download feed with a feed reader / - make sure it updates daily

## Sprint backlog
Sprint Backlog

Feature	Remaining	Task

View lastest jobs from top ruby sites	4	Index 1 feed
	1	Collate all top feeds
	1	Index all feeds
	2	Display all job posts
	2	Paginate results
	1	Display summary of job post

Search top ruby sites jobs for last 3 months	5	Boolean AND search
	2	Paginate results
	1	Results in reverse date order
	8	Display exerpts in results
	4	Highlight matching terms in results

	31

## Sprint burndown
Mon 20 Jul	37	37
Tue 21 Jul	37	37
Wed 22 Jul	35.5	37
Thu 23 Jul	34	37
Fri 24 Jul	32.5	37
Sat 25 Jul	31	37
Mon 27 Jul	28	37
Tue 28 Jul	26.5	37
Wed 29 Jul	25	37
Thu 30 Jul	23.5	37
Fri 31 Jul	22	37
Sat 1 Aug	20.5	37
Mon 3 Aug	17.5	37
Tue 4 Aug	16	37
Wed 5 Aug	14.5	31
Thu 6 Aug	13	28
Fri 7 Aug	11.5	25
Sat 8 Aug	10	22
Mon 10 Aug	7	19
Tue 11 Aug	5.5	16
Wed 12 Aug	4	13
Thu 13 Aug	2.5	10
Fri 14 Aug	1	7
Sat 15 Aug	-0.5	4